## test_coverage
High Priority test cases written | 259 | Test cases written | 405
High Priority test cases not yet written | 0 | Test cases not yet written | 2

## Progress
Iteration | Remaining LOE for High Priority Tasks | Remaining LOE for All Tasks
0 | 289 | 501
1 | 252 | 454
2 | 165 | 365
3 | 51 | 251
4 | 26 | 157
5 | 26 | 140
6 | 10 | 88
7 | 5 | 24
8 | 5 | 8

## Velocity
Iteration | Velocity
1 | 47
2 | 89
3 | 114
4 | 94
5 | 17
6 | 52
7 | 64
8 | 16