# caArray-caIntegrator – Status Meeting Minutes

**December 13, 2011**

## Attendees:

|  |  |  |  |
| --- | --- | --- | --- |
| Andy Evans |  | Mervi Heiskanen | Y |
| Cuong Nguyen | Y | Michael Benham | Y |
| Deb Hope | Y | Quy Phung | Y |
| Don Swan | Y | Rashmi Srinivasa | Y |
| Eve Shalley | Y | Robert Shirley |  |
| Henry Schaefer | Y | Shine Jacob | Y |
| Jacob Mensah | Y | Tony Kerlavage |  |
| Jill Hadfield | Y | Will Fitzhugh | Y |
| JJ Pan | Y | Xiaopeng Bian | Y |
| JP Marple | Y | Yeon Choi |  |
| Juli Klemm | Y | Zhong Li | Y |
| Larry Brem | Y |  |  |
| Maki Duncan |  |  |  |

## Discussion:

### caArray:

* caArray 2.5.0 status:
  + Design tasks: Complete. (Were discussed at the end of the meeting.)
    - Remote file locations (ARRAY-2156). No-go decision made.
    - Permissions for TRANSCEND (ARRAY-2196).
  + Bug fixes: ARRAY-2167 is Complete; ARRAY-2149 is In Progress.
  + BDALite: AHP3 track setup by Systems team is In Progress.
    - Change to database properties configuration requested by the Systems team. New issue created: ARRAY-2197.
  + Test suite updates and test plan review items have been added to the project plan.
* Project plan is here: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_Project_Plan.mpp>

### caIntegrator:

* Version 1.4 - Tech Stack Upgrade – In Progress.
  + Working with systems team to setup AHP build track.
  + ETA will be helpful from system team. Mick Benham will check on ETA.
  + Nightly builds fails now
  + No deployment to Prod until we have everything setup to work with new tech stack, AHP3.0 etc.
* Other activities
  + Xenoline update: Waiting for COTR/NCI response.
  + caDSR requirements. Larry will look into permissible values in LexEVS. Meeting with the caDSR team this week.
  + Other maintenance and bug fixes.
* Updated project plan is here: [https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project\_management/caintegrator\_project\_plan.mpp](https://ncisvn.nci.nih.gov/svn/caintegrator2/trunk/docs/project_management/caintegrator_project_plan.mpp" \t "_blank)

### TRANSCEND:

* Permissions design: was discussed today.
  + The team will set up a meeting with Santosh’s team to review the architectural approach for this. Will wait to set up a meeting with Sarah until approach has been decided on.
* Setting up caIntegrator sample studies to use the caArray sample experiments.
* Study Archive – started.
* Eve will create an overall TRANSCEND project plan with milestones from each project and dependencies between projects. Monthly all-hands TRANSCEND technical meetings will start in January.

### Systems and DBA:

* The Systems team will get back to the caIntegrator team re: ETA for tech stack upgrades and AHP 3 setup.

### Documentation:

* No updates this week.

### Support and Knowledge Center:

* Added Google citation alerts for caArray and caIntegrator.

## Open Action Items:

* Full list of closed and current action items are available here: <https://ncisvn.nci.nih.gov/svn/caarray2/trunk/docs/project_management/caArray_caIntegrator_Action_Items.xlsx>

| **Item #** | **Description** | **Responsible Party** | **Date Identified** | **Disposition** |
| --- | --- | --- | --- | --- |
| 5. | Set up a meeting to discuss caGrid 1.2 upgrade | Shine Jacob | 8/4/2011 | Not Started |
| 13. | caArray and caIntegrator demos for JJ | Rashmi Srinivasa and Shine Jacob | 9/6/2011 | Complete |
| 14. | Talk to the UPT team re: dissuading caArray users from creating groups within UPT. | JJ Pan and Larry Brem | 9/6/2011 | In Progress (UPT team working on it) |
| 23. | Update permissions wireframes for TRANSCEND to reflect the latest understanding of the data. | Andy Evans | 11/15/2011 | Not Started |
| 24. | Set up regular once-in-2-weeks meetings with TRANSCEND | Eve Shalley | 11/30/2011 | In Progress |
| 25. | Set up a meeting with the caDSR team to discuss permissible values. | Mervi Heiskanen | 12/6/2011 | Complete |
| 26. | Set up an internal meeting to evaluate alternative approaches to setting permissions (common UI versus changes to individual apps) | Rashmi Srinivasa | 12/6/2011 | Complete |